## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2221-swen-610-01-d power rangers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Customer, I want to login to the E-Store, Using username and password, to buy learning material online. | Given I Click the login button, When the backend is up and running Then the system should displays a popup to enter credentials.
GIVEN I submit my credentials, WHEN a user with the given name already exists THEN the system should login me and the UI must redirect me to the home page
GIVEN I submit my credentials, WHEN no user with the given name exists THEN the system should Return User Not found Error and this must be displayed in the UI.
As an Admin, I want to login to E-store with admin username and admin password, to manage inventory and user permissions. | Given I login with reserved username admin, WHEN my credentials are in the admin data and not user data, THEN website must display a button called admin to allow me to add, delete, modify products.
Given I Click the login button, When the backend is up and running Then the system should displays a page to enter credentials.
GIVEN I submit a credentials object WHEN a user with the given name already exists THEN the system should login me and the UI must redirect me to the Product list page.
As an Admin, I want to remove products that are no longer procured from inventory register, to make sure they are not diaplayed to the customer. | Given I want to remove an item to the inventory, When the item is in the inventory, THEN I must be able to remove successfully by clicking the delete buttion beside product in the admin page.
Given I want remove to an item from the inventory, When the item is not in the inventory, System must Then not display the item in delete list.
As an Admin, I want to edit product data, So that I can maintain latest information on the website. | Given I want to edit information of an item in the inventory, When the item is not in the inventory, THEN the system must not display the item in the edit list of admin page.
Given I want to edit information of an item in the inventory, When the item is in the inventory, System must update the specific information of the item based on form data entered (after clicking the edid button on admin page)
As an Admin, I want to add new products to the inventory, so that they will be automatically listed on the E-Store. | Given I want to add a new item to the inventory, THEN I must be able to add successfully using a form.
As a Customer, I would want to search by typing in topic of study, to list down related material. | GIVEN I type a name or part of the name in the field provided on website, WHEN the name is part of any product name in the product catalog, THEN I must be able to view the list of matching products on the UI
GIVEN I type a name or part of the name in the field provided on website, WHEN the name is part not part of any product name in the product catalog, THEN I must not see any product listed.
As a Customer, I want to remove products to my shopping cart, to update the items in cart. | Given I click remove beside any product name in cart, WHEN the product is in the cart, Then the System must remove the item from cart and reduce the total price displayed.
As a Customer, I want to view the current items in my cart, to check-out | Given I click on the cart button in the navigation bar, I must be redirected to the cart Page.
GIVEN i am in the cart page, WHEN there are items added to the cart, Then I must be able to view the items, total price and a remove buttons.
Given I am in the cart page, WHEN there are no items added to the cart, Then I must see a message "no items added to the cart".
As a Customer, I want to add products to my shopping cart, to update the items in cart. | Given I click add to cart button beside any product name, WHEN the product is not in the cart, Then the System must add the item to cart and update the total price
Given I click add to cart button beside any product name, WHEN the product is not in the cart, Then the System must increase the item count and update the total price
As a Customer, I would want to filter by product rating or price range, to refine the list of relate material. | Given a customer clicks sort button, then the UI must display option (popup) sort products by price or rating
Given I click on sort by price, it displays all product starting with lowest price first
Given I click on sort by rating, it displays all product starting with highest rating first
As a Customer, I would want to choose between one or all types of material (Video, Book) to refine the list of material displayed. | GIVEN I am in a home Page WHEN a filter(video,audio,books) is clicked from homepage THEN the system should show the products according to the filter(video,audio,books)
GIVEN I am in a home Page WHEN a filter named "All" is pressed THEN the system should show all the products
GIVEN I am in a home Page WHEN a filter (video,audio,books) is clicked and no products matchs the filter THEN the system should show empty page stating no "Audio/Video/Book" are found.
As a Customer, I would want to view the average rating of author (for all his products) of the product I choose, to make decision of adding product (material) to cart. | GIVEN I am in a product Page, THEN the author name must be clickable
GIVEN I am in a product Page WHEN the author name is clicked THEN the system should show the author detail page
As a Customer, I want to retain Customer information even if I logout, to avoid re-entering | GIVEN I login and perform an action WHEN I logout and login again THEN the system should retain my information in cart
As an Author, I would want to login using admin provided username and password, to manage my content and profile, for increasing my product sales. | Given I login with reserved username for author, WHEN my credentials are in the author data and not user data, THEN backend System must allow me to update profile and request admin for new product.
Given I Click the login button, When the backend is up and running Then the system should displays a popup to enter credentials.
GIVEN I submit a credentials object WHEN a user with the given name already exists THEN the system should login me and return a status code of 200 (OK) and the UI must redirect me to the Product list page.
GIVEN I submit a credentials object WHEN no author with the given name exists THEN the system should Return User Not found Error and this must be displayed in the UI.
As an admin, I want to review and approve profile change and product addition/update requests from Authors, to update their profile or listing on E-Store. | GIVEN I am logged in as an Admin, When Author requested to introduce a new product, Then I must be able to approve and add the product.
Given I am logged in as Admin, When there are authors with profiles updated, I must be able to view, edit and delete profiles of authors.
GIVEN I am logged in as an Admin, When Author requested to update profile, Then I must be able to approve and add the product.
As an author, I want to raise request to revise/update my content (videos/books/audios) on the E-store, so that admin can review and approve it. | Given I am logged in as Author, Then I must have a form to raise request for admin adding my new product.
Given I am logged in as Author, When I have requests for approval, Then I must be able to notify admin for request approvals.
As a Customer, if author supports one-on-one sessions, I would want to view and add a one-to-one session to cart, for checking out. (8) | GIVEN I'm in homepage WHEN there are available one-to-one sessions, I must be able to see all the one-to-one sessions.
GIVEN I click the add button of an one-to-one session, WHEN the product is not in the cart, THEN the system must add the item to cart. (back end should log 200 ok)
GIVEN I click the add button of an one-to-one session, WHEN the product is already in the cart, THEN the system should not increment the count.
As a Customer, I want to add one-on-one session to cart like any other product, to purchase and access video session link. | GIVEN I check out successfully, WHEN there are one-to-one sessions in my cart, I should have access to the session links.